From Maternity Care Deserts to a Siting Plan: A Block-Level Decision Platform for Obstetric Access in Texas

Applicant organization: Austin College, Sherman, Texas

Principal Investigator: Md Mohsan Khudri, PhD, Assistant Professor of Economics

Amount requested: $29,150

Significance

Texas has the largest population of reproductive-age women of any state without a

statewide obstetric access standard. Maternal mortality rose 63% between 2018 and

2020, and most of those deaths were judged preventable (Texas Women's Healthcare

Coalition, 2024). Where a woman lives determines whether she reaches skilled care

in time.

The standard measure of that risk — the "maternity care desert," a county with no

obstetric facility — is too coarse to act on. Texas counties range from 386 to

16,040 km², so averaging access across one hides exactly the variation a planner

needs, and the measure cannot distinguish a county that never had a hospital from

one whose hospital closed its labor-and-delivery unit.

We have already built the measurement that replaces it. On the complete Texas

road network we computed drive time and road distance from **every one of the

668,757 census blocks** to the nearest hospital that actually provides obstetric

care, weighted by women aged 15–44 (ACS 2019–2023, table B01001). Complete,

not sampled:

| Finding | Value |
| --- | --- |
| Active hospitals providing obstetrics on site | 211 |
| Counties with no obstetric facility | 151 of 254 |
| Women aged 15–44 in Texas | 6,180,678 |
| Women 15–44 more than 30 min from obstetric care | 185,251 (3.0%) |
| Women 15–44 more than 30 min from NICU-capable care | 576,262 (9.4%) |
| Counties with a hospital but no obstetric unit | 78 (1.73M residents) |

Against the planning benchmarks the field uses:

| Benchmark | Women 15–44 within it |
| --- | --- |
| 25 miles of an obstetric facility | 95.9% |
| 35 miles | 98.6% |
| 50 miles | 99.7% |
| 30 minutes | 97.0% |
| 30 minutes of a NICU-capable facility | 90.6% |

Two findings drive this proposal.

First, the level of care. By distance to any obstetric facility Texas looks

adequate. Measured against facilities with a neonatal intensive care unit —

the capability that decides outcomes in a preterm birth or hemorrhage — the share

of women left beyond 30 minutes is three times larger (9.4% vs 3.0%). Panels

(a) and (b) of Figure 1 use an identical mileage scale, so the gap reads directly:

**5.1% of Texans are more than 25 road miles from any obstetric facility, but

13.0% are that far from one with a NICU; past 50 miles the ratio widens

eleven-fold.** Proximity to a door is not proximity to care, and that gap is

exactly where preventable deaths occur.

Second, 78 counties have an open hospital where no one can deliver a baby,

home to 1.73 million Texans. These do not need a new hospital — they need an

obstetric unit restored inside one that already exists, at a fraction of the cost.

**No county-level desert map can see this distinction, and every published Texas

desert map misses it.** It is the cheapest available intervention, and nobody can

currently target it.

Figure 1 — The access landscape. (a) Road miles to the nearest obstetric

facility. (b) Road miles to the nearest NICU-capable facility, on the identical

scale — directly comparable, and visibly darker. (c) Population by road-distance

band. (d) Counties with a hospital but no obstetric unit (gold) versus counties

with no hospital at all (pink).

Innovation

**1. We measure at census-block resolution on the real road network, not by

county and not in straight lines.** Our preliminary analysis shows road distance

in Texas is on average 1.33× the straight-line distance, and considerably

worse in the sparse western road grid (Figure 3a). Buffer- and centroid-based

studies — still the norm in this literature — understate real travel by a third.

2. We solved the computational obstacle that forces others to approximate.

Naively, 668,757 blocks against 211 facilities is 141 million origin–destination

pairs — which commercial routing APIs cannot price, and why comparable studies

sample, aggregate to counties, or fall back on straight lines. Because only the

nearest facility matters, a single **multi-source Dijkstra search on the

transposed road graph** labels every node in Texas with its cost to the closest

facility in one pass — about three seconds over 11.0 million nodes and 21.6

million road segments. No API, no quota, no sampling, no recurring cost. This is

what makes an interactive planning tool possible at all.

3. We correct a failure mode that silently distorts this entire literature.

Facility lists are built by joining a services registry to a location registry on

hospital name. The project's own prior list used an exact string match, which

dropped 36% of eligible hospitals while retaining hospitals that had already

closed. This is not random noise: **every dropped hospital manufactures a fake

desert.** Our multi-stage matcher — license ID, then street address, then

normalized fuzzy name, each blocked geographically — recovers 98.1% automatically

(Figure 3b), moving the count of Texans beyond 30 minutes from 2.58 million to

1.06 million. **A desert map built on an uncorrected join is wrong by a factor of

two.** We will release the matcher as a reusable component.

4. The deliverable is a decision tool, not a paper. The end product is a

web-based planning platform where a state or county planner sets a budget and a

coverage standard and receives a ranked, mapped siting plan with the population

served by each candidate site.

Approach

Aim 1 — Publish the corrected Texas obstetric access baseline *(months 1–4)*

The pipeline is built and runs end to end, and the women 15–44 denominator is

already in place. Remaining work: validate free-flow travel times against a

commercial routing engine on a stratified sample of ~500 routes; extend the

facility panel backward through Centers for Medicare & Medicaid Services (CMS)

Provider of Services archives so the analysis

dates obstetric-unit closures rather than describing a single snapshot; and

disaggregate the ACS denominator below block-group level, which currently assumes

a uniform age–sex mix within each block group. Deliverable: peer-reviewed

paper and a public dataset of block-level access for all 668,757 Texas blocks.

Aim 2 — Optimize where the next facility goes *(months 3–9)*

We formulate siting as the Maximal Covering Location Problem: choose K sites

maximizing the underserved population brought within a coverage standard.

Candidates are restricted to existing incorporated places — a hospital needs

staff, utilities and road access, so an optimum in empty rangeland is not a usable

answer.

This already works. Figure 2 shows the current output: **ten new facilities

would bring 72,737 of the 178,685 underserved women aged 15–44 within 30 minutes

— 40.7% of the gap.** Because coverage is monotone submodular, the greedy solution

carries a provable (1 − 1/e) ≈ 63% approximation guarantee — a bounded result, not

a heuristic guess.

Grant work extends this baseline in three directions:

Cost-aware ILP. Replace "K facilities" with a real budget. Restoring an

obstetric unit in an existing hospital and building a new facility differ by

more than an order of magnitude in cost; the 78 hospital-but-no-obstetrics

counties are the cheap wins, and the model must be able to say so.

Capacity, via two-step floating catchment area (2SFCA). Proximity ignores

whether the nearest facility can absorb the demand; bed counts and staffing are

already in our data.

**Sequential siting under uncertainty — where reinforcement learning earns its

place.** For a static problem ILP beats RL, and we will not pretend otherwise.

But the real problem is not static: facilities are funded over several years,

populations shift, and units continue to close. That is a sequential decision

problem under uncertainty, the setting where an RL policy genuinely outperforms

re-solving a deterministic program. We will benchmark RL against the ILP optimum

and report the comparison honestly, including if RL does not win.

Figure 2 — From diagnosis to decision. (a) The ten highest-impact sites over

territory where women 15–44 are beyond 30 minutes. (b) Coverage versus number of

facilities — the curve that lets a funder choose a defensible stopping point.

Aim 3 — Release the planning platform *(months 8–12)*

A browser tool, free and public: set budget and coverage standard, choose whether

to weight by women of reproductive age (the default) or all residents, target any

obstetric facility or only NICU-capable ones, and receive a ranked siting plan with a map

and an exportable table. Every input dataset is public, every step scripted, and

the code released under an open license so any state can rerun it. Texas is the

test case; the method is portable to all fifty states.

Figure 3 — Why the method matters. (a) Road travel exceeds straight-line

distance by 1.33× on average, population-weighted. (b) What correcting the

facility list changed.

Risks and mitigation

| Risk | Mitigation |
| --- | --- |
| CMS obstetric-service flags lag real closures | Cross-check against Texas Department of State Health Services (DSHS) maternal designations and the American Hospital Association (AHA) Annual Survey; report the vintage of every flag |
| Free-flow travel times ignore congestion | Aim 1 calibrates against a commercial routing engine; distance results are unaffected |
| RL underperforms ILP | Explicitly an experimental comparison, not an assumption; ILP is the shipped default |
| Cross-border access unmodeled | Extend the network extract to bordering states for border counties |

Benchmarks for success

Block-level access dataset published, all 668,757 blocks (month 4)

Travel-time validation r ≥ 0.95 against a commercial routing engine (month 5)

ILP and RL benchmarked against the greedy bound (month 9)

Public platform live with ≥ 3 named agency or advocacy users (month 12)

One manuscript submitted; code and data publicly archived (month 12)

Investigator(s)

Md Mohsan Khudri, PhD, Assistant Professor of Economics at Austin College,

will serve as Principal Investigator. He will provide overall leadership,

direct the research, supervise the project team, and ensure compliance with

ethical standards, institutional policies, and conflict-of-interest

requirements. Dr. Khudri will oversee data acquisition, security, sharing, and

authorship practices, and will maintain clear communication with Austin College

and the Foundation. As a health economist, he will guide the study design,

monitor progress toward project milestones and deliverables, lead development of

the analytical model, and translate the findings into policy-relevant

recommendations.

Navid Mohammad Imran, PhD, Assistant Professor of Computer Science at

William Paterson University of New Jersey, will serve as **Co-Principal

Investigator**. Dr. Imran brings specialized research expertise in machine

learning, combinatorial optimization, and algorithmic modeling for complex

spatial and dynamic decision systems. He will lead the core technical

architecture of the project, overseeing formulation of the cost-aware Integer

Linear Programming models, development and training of the reinforcement

learning framework, and the computational pipeline supporting the interactive

decision platform.

Alamgir Hosain, PhD, Research Scientist at EnviTrace, Santa Fe, New Mexico,

will serve as Co-Principal Investigator. His primary responsibilities will

include data collection and management, processing and feeding the datasets to

the model, contributing to model development, and developing the software

packages that turn the results into a practical tool. As a computational

geoscientist, Dr. Hosain will oversee characterization of the geographic

distribution of maternity care deserts, identification of prospective locations

for new facilities, and the probabilistic approach to varying population

coverage under minimal use of economic resources. He built the preliminary study

underpinning this proposal — the corrected facility registry, the

11-million-node road network, and the routing engine.

Budget

Indirect costs are limited to 10% of the total budget, per Foundation guidelines.

| Line item | Amount |
| --- | --- |
| PI summer salary (1 month) | $7,500 |
| Co-investigator stipends (3 × $2,500) | $7,500 |
| Graduate research assistant (10 months, part time) | $6,000 |
| Cloud compute and storage | $1,200 |
| Platform hosting and domain (3 years) | $900 |
| Routing-engine validation credits and data | $1,135 |
| Dissemination (one conference, open-access fee) | $2,000 |
| Total direct costs | $26,235 |
| Indirect costs (10% of total) | $2,915 |
| Total requested | $29,150 |

Austin College provides in-kind analytics lab access, secure storage, computing,

seminar space, staff support, and pre- and post-award administration. No matching

or pending funds are committed to this project.

Resources

Austin College endorses this project and will support it through the grant period,

maintaining access to the analytics lab, seminar space, and secure storage, and

providing IT support, account provisioning, and purchasing. The IRB and data

governance offices will guide human-subjects review and data use agreements; the

project uses only public, de-identified aggregate data and is expected to qualify

as non-human-subjects research.

All computation to date has run on standard hardware — the full statewide analysis

completes in under ten minutes on a laptop — so the project carries no

high-performance computing dependency and no recurring API cost.

Data sources

All inputs are public. US Census Bureau TIGER/Line 2024, 2020 Decennial

population and ACS 2019–2023 (public domain); Census 2020 Centers of Population;

CMS Provider of Services file (obstetric and neonatal service codes); HIFLD

hospital locations;

and OpenStreetMap via Geofabrik for the road network (ODbL — © OpenStreetMap

contributors), verified against the publisher's published MD5 checksum.

References

American College of Obstetricians and Gynecologists & Society for Maternal–Fetal

Medicine. (2019). Levels of maternal care (Obstetric Care Consensus No. 9).

Centers for Disease Control and Prevention, National Center for Health Statistics.

(2023). Maternal mortality rates in the United States, 2021.

Chartis Center for Rural Health. (2024). *Unrelenting pressure pushes rural safety

net crisis into uncharted territory.*

Church, R., & ReVelle, C. (1974). The maximal covering location problem. *Papers in

Regional Science, 32*(1), 101–118.

Luo, W., & Qi, Y. (2009). An enhanced two-step floating catchment area (E2SFCA)

method for measuring spatial accessibility to primary care physicians. *Health &

Place, 15*(4), 1100–1107.

March of Dimes. (2023). Where you live matters: Maternity care in Texas.

Meredith, M. E., Steimle, L. N., & Radke, S. M. (2024). The implications of using

maternity care deserts to measure progress in access to obstetric care: A

mixed-integer optimization analysis. BMC Health Services Research, 24, 682.

Nemhauser, G. L., Wolsey, L. A., & Fisher, M. L. (1978). An analysis of

approximations for maximizing submodular set functions. *Mathematical Programming,

14*(1), 265–294.

Texas Administrative Code, 25 TAC §§133.208–133.209. *Maternal designation

Levels III and IV.*

Texas Women's Healthcare Coalition. (2024). *Texas releases 2024 maternal health

report.*

U.S. Government Accountability Office. (2022). *Availability of hospital-based

obstetric care in rural areas* (GAO-23-105515).